## Brief
Build a campaign you can review
Fictional example: invented project, dates, work and USD allowances. These are not market prices, publisher offers or achieved results. Edited examples retain this label until cleared.
Fill the Brief, then the Budget. Blank costs are unknown; zero means a recorded zero. Money and hours are separate. The summary counts missing amounts and shows known subtotals for the 12 work rows. Keep one currency and re-enter values if you change it. Use Review only for observations actually made.
Purpose and selection | Planning draft — not approval or observed results
Campaign name | Bicycle brake checklist — pilot
Reader outcome and objective | Make a useful brake-inspection checklist and test whether a small, relevant group of cycling editors finds it useful. No link, traffic or ranking target is assumed.
Owned destination URL | https://example.com/guides/brake-check
Audience and context | People checking a commuter bicycle before a ride; editors of practical cycling resources.
Selection criteria and exclusions | An identifiable editor, a relevant maintenance section and a real reader need. Exclude unrelated directories, undisclosed paid references and promises of guaranteed rankings.
Responsible owner | Fictional project editor
Planned start | 2030-04-01
Planned review | 2030-04-15
Planned end | 2030-04-30
Baseline and evidence method | Before contacting anyone, record the destination’s readiness and available referral baseline. At review, compare actual replies, published pages and measured visits separately; leave unavailable data blank.
Pause or revise when… | Pause if the checklist is incomplete, the proposed page is irrelevant or projected spending exceeds USD 400. Change the scope before authorizing extra cost.
Currency | USD
Spending limit | 400

## Budget
Build a campaign you can review
Fictional example: invented project, dates, work and USD allowances. These are not market prices, publisher offers or achieved results. Edited examples retain this label until cleared.
Fill the Brief, then the Budget. Blank costs are unknown; zero means a recorded zero. Money and hours are separate. The summary counts missing amounts and shows known subtotals for the 12 work rows. Keep one currency and re-enter values if you change it. Use Review only for observations actually made.
Work to deliver | Responsible owner | Planned due date | Estimated cost | Committed cost | Actual spend | Estimated hours | Estimate basis / evidence notes
Inspect and edit the destination | Fictional editor | 2030-04-03 | 80 |  |  | 3 | Invented USD 80 allowance; 3 hours are an effort estimate, not an additional charge. | 1 | 0
Create and check the illustrations | Fictional designer | 2030-04-08 | 160 |  |  | 6 | Invented USD 160 allowance; verify instructions and accessibility before outreach. | 1 | 0
Research a small relevant editor list | Fictional researcher | 2030-04-12 | 40 |  |  | 4 | Invented USD 40 allowance; manual suitability research, no bought contact list. | 1 | 0
Review replies and delivery evidence | Fictional reviewer | 2030-04-30 | 40 |  |  | 2 | Invented USD 40 allowance. No paid placement is included; any sponsorship needs separate terms and review. | 1 | 0
[8 empty] | 0 | 0
[8 empty] | 0 | 0
[8 empty] | 0 | 0
[8 empty] | 0 | 0
[8 empty] | 0 | 0
[8 empty] | 0 | 0
[8 empty] | 0 | 0
[8 empty] | 0 | 0
Budget overview | [8 empty] | 0
Currency | USD |  | Estimated cost | Committed cost | Actual spend | Estimated hours
Known subtotal |  |  | 320 | 0 | 0 | 15
Unrecorded items |  |  | 0 | 4 | 4 | 0
Unallocated planned budget |  |  | 80
All money uses the selected currency. Changing the currency does not convert numbers. Use 0.50 or 0,50 without thousands separators; JPY accepts whole units. Hours stay separate and are not added to money.
A valid draft is not a complete or approved campaign. Unknown costs remain unknown. Dates are planning dates; record actual evidence and decisions separately. A cost total does not predict links, visits or rankings.

## Review
Build a campaign you can review
Fictional example: invented project, dates, work and USD allowances. These are not market prices, publisher offers or achieved results. Edited examples retain this label until cleared.
Fill the Brief, then the Budget. Blank costs are unknown; zero means a recorded zero. Money and hours are separate. The summary counts missing amounts and shows known subtotals for the 12 work rows. Keep one currency and re-enter values if you change it. Use Review only for observations actually made.
Observed on | Evidence reference | Observed outcome | Decision and reason | Reviewer | Next review date